## Sheet1
Grouping | Category | Findings Statement | Recommendation | Type/Severity | GitHub issue | Status
Homepage | Navigation | Participants had an easier time finding the query tool links than in previous studies, but didn't always know what they would lead to. | Make links to the query tool consistent. | Medium | https://github.com/ONRR/nrrd/issues/316 | Closed
Homepage |  | Participants liked the new homepage and found the links to the query tool. Participants would like more detailed Native American information | Investiate adding detailed Native American data | Medium
Query Tool | Bug | Participants are having trouble seeing the available data. | Format columns to show content properly | High | https://github.com/ONRR/nrrd/issues/351 | Closed
Query Tool | Bugs | A bug is causing group by to not list out the states | Fix group by to list out all states | High | https://github.com/ONRR/nrrd/issues/421 | closed
Query Tool | Bugs | Participants weren't able to figure out how to group by commodity because it was selected in the breakout by drop-down and, therefore, removed from the group by drop-down. | Include all options in the group by drop-down. | Medium | https://github.com/ONRR/nrrd/issues/355 | open
Query Tool | Content | Participants want details we have in the documentation available from the query tool. | Put links to documentation back in. | High | https://github.com/ONRR/nrrd/issues/431 | open
Query Tool | Content | Participants want clarification of year. | Clarify if data if FY or CY | High | Should be fixed on its own when we clean up the data.
Query Tool | Content | Participants want to see energy related commodities first in the filter options and table. | List energy related commodities first | Medium | https://github.com/ONRR/nrrd/issues/346 | open
Query Tool | Content | Participants want monthly data. | Add in monthly data at a later time | Medium | https://github.com/ONRR/nrrd/issues/96
Query Tool | Content | Participants want to see summary data. | Show a row of summary data | Low | https://github.com/ONRR/nrrd/issues/353
Query Tool | Content | Participants want disposition code and more Native American data. | Study adding disposition code to add breakdown between tribal and allottee data. | Low
Query Tool | Filter Data | Participants didn't notice the filter data button. | Make filter button more prominent | High | https://github.com/ONRR/nrrd/issues/350 | Open
Query Tool | Filter Data | Participants didn't understand the difference between land class and land category. | Combine land class and land category into one field. | High | https://github.com/ONRR/nrrd/issues/423 | closed
Query Tool | Filter Data | Participants expected there to be an apply button to close the filter drawer. | Add an apply button | High | https://github.com/ONRR/nrrd/issues/349 https://github.com/ONRR/nrrd/issues/333
Query Tool | Filter Data | Participants wanted an option to select "all" for some of the filters. | Add "all" option to filters. | Medium | https://github.com/ONRR/nrrd/issues/463
Query Tool | Filter Data | Year slider doesn't show what year you're on. | Add year to slider like on Explore Data. | Medium | https://github.com/ONRR/nrrd/issues/444
Query Tool | Filter Data | Participants wanted to see the filters before the data. | Consider whether it makes sense to open the filters before showing the data. | Medium | https://github.com/ONRR/nrrd/issues/445
Query Tool | Query Table format | Participants are confused by expansion options. | Default to only one level and don't show expand/collapse when there's only one level. | High | https://github.com/ONRR/nrrd/issues/359 https://github.com/ONRR/nrrd/issues/358
Query Tool | Query Table format | Participants were confused by the two scoll bars | Removed horizontal scroll bar by minmizing the number of years that automatically display | High | https://github.com/ONRR/nrrd/issues/347 | closed
Query Tool | Download | Participants want to be able to export filtered view | Add download option | High | https://github.com/ONRR/nrrd/issues/87 | closed
Query Tool | Disbursments | Participants want more disbursements information | None | N/A
Explore Data | Nationwide | Participant thought could only see state data not nationwide data a | Make sure it's clear that nationwide data is available. | High | https://github.com/ONRR/nrrd/issues/324
Explore Data |  | Participant noted the that the timeline is flipped from explore data | Make consistent timelines | High | https://github.com/ONRR/nrrd/issues/354
Explore Data |  | Participant wanted more information about revenue types | Add a ? mark link to revenue type definition | High | https://github.com/ONRR/nrrd/issues/289
Explore Data | State Cards | Participants expected to be able to click on the cards and get more details. | Have the page scroll to comparison section when clicking on cards. | Medium | https://github.com/ONRR/nrrd/issues/325
Explore Data | Circle Charts | Participants had a hard time differentiating colors on circle charts. | Explore options for better contrast. | Medium
Explore Data | Query Tool Connection | Participants would be impressed if filter view from query tool would carry over to explore data but wouldn't expect it | Leave as is due to time constraints | N/A
Explore Data | State Cards | Positive findings
Explore Data |  | Participant thought there was too much information | none | N/A
Explore Data | Map
Content | Oil & Gas | Participants are specifically unclear about what "oil and gas" means and would like more explanation of data. | Include a ? mark button to define "oil and gas", and to define revenue types | High | https://github.com/ONRR/nrrd/issues/446
Ease of use | Explanations | P2: Suggested explaining to the user how the site functions and not rely on icons to be self explantory.
Data Availability |  | Participants want more granular data | Continue to investigate adding more granular data | Medium
IE |  | Participants had trouble seeing query tool options in IE | Fix bugs | Medium | https://github.com/ONRR/nrrd/issues/387 https://github.com/ONRR/nrrd/issues/447
Outreach |  | Participants are intertested in knowing more about how to find our data | Investigate outreach activities | Medium
Tasks |  | Tasks | None | N/A
Note on F12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I think this will be solved by having labels on the total rows.